## Activity Plan
ACTIVITY PLAN
Weekly Progress Tracking Dashboard ¦ Generated: November 25, 2025
✓ | Done | ● | Ongoing | ○ | Planned | ! | Delayed | ↻ | Re-sch | ⏸ | On Hold
[6 empty] | WW46 | [6 empty] | WW47 | [6 empty] | WW48 | [6 empty] | WW49 | [6 empty] | WW50 | [6 empty] | WW51
[6 empty] | 10 Mon | 11 Tue | 12 Wed | 13 Thu | 14 Fri | 15 Sat | 16 Sun | 17 Mon | 18 Tue | 19 Wed | 20 Thu | 21 Fri | 22 Sat | 23 Sun | 24 Mon | 25 Tue | 26 Wed | 27 Thu | 28 Fri | 29 Sat | 30 Sun | 01 Mon | 02 Tue | 03 Wed | 04 Thu | 05 Fri | 06 Sat | 07 Sun | 08 Mon | 09 Tue | 10 Wed | 11 Thu | 12 Fri | 13 Sat | 14 Sun | 15 Mon | 16 Tue | 17 Wed | 18 Thu | 19 Fri | 20 Sat | 21 Sun
No. | ID | Activity / Task Description | Start | End | Status
10 | Plate Particle Cleaning Evaluation
1 | 10.1 | Cleaning 3 pieces of plate with cleaning methods from 3 Pdoc | 10-Nov | 11-Nov | ✓ Done | bar: WW46 10 Mon to WW46 11 Tue; WW48 25 Tue
2 | 10.2 | Cleaning another 3 pieces recovered by Kasahara-san | 11-Nov | 12-Nov | ✓ Done | bar: WW46 10 Mon to WW46 14 Fri; WW47 17 Mon to WW47 21 Fri; WW48 24 Mon to WW48 28 Fri; WW49 01 Mon to WW49 05 Fri; WW50 08 Mon to WW50 12 Fri; WW51 15 Mon to WW51 19 Fri
3 | 10.3 | Give the 3 pieces result to Kasahara-san & Kamei-san | 12-Nov | 12-Nov | ✓ Done | bar: WW46 12 Wed; WW48 25 Tue
4 | 10.4 | For review with Kasajima san & Kami san | 13-Nov | 13-Nov | ✓ Done | bar: WW46 10 Mon to WW46 14 Fri; WW47 17 Mon to WW47 21 Fri; WW48 24 Mon to WW48 28 Fri; WW49 01 Mon to WW49 05 Fri; WW50 08 Mon to WW50 12 Fri; WW51 15 Mon to WW51 19 Fri
5 | 10.5 | Implemented in the system - Fullscreen + Autostart | 17-Nov | 18-Nov | ✓ Done | bar: WW47 17 Mon to WW47 18 Tue; WW48 25 Tue
6 | 10.6 | Modifying new features | 19-Nov | 20-Nov | ● Ongoing | bar: WW46 10 Mon to WW46 14 Fri; WW47 17 Mon to WW47 21 Fri; WW48 24 Mon to WW48 28 Fri; WW49 01 Mon to WW49 05 Fri; WW50 08 Mon to WW50 12 Fri; WW51 15 Mon to WW51 19 Fri
7 | 10.7 | Modifying main command program | 24-Nov | 26-Nov | ○ Plan | bar: WW48 24 Mon to WW48 26 Wed
8 | 10.8 | Adjustment to the scanning functions | 27-Nov | 28-Nov | ○ Plan | bar: WW46 10 Mon to WW46 14 Fri; WW47 17 Mon to WW47 21 Fri; WW48 24 Mon to WW48 28 Fri; WW49 01 Mon to WW49 05 Fri; WW50 08 Mon to WW50 12 Fri; WW51 15 Mon to WW51 19 Fri
11 | Auto Coil Winding Improvement
1 | 11.1 | Initial assessment and planning | 17-Nov | 18-Nov | ✓ Done | bar: WW47 17 Mon to WW47 18 Tue; WW48 25 Tue
2 | 11.2 | Design modifications review | 19-Nov | 21-Nov | ● Ongoing | bar: WW46 10 Mon to WW46 14 Fri; WW47 17 Mon to WW47 21 Fri; WW48 24 Mon to WW48 28 Fri; WW49 01 Mon to WW49 05 Fri; WW50 08 Mon to WW50 12 Fri; WW51 15 Mon to WW51 19 Fri
3 | 11.3 | Implementation of changes | 24-Nov | 28-Nov | ○ Plan | bar: WW48 24 Mon to WW48 28 Fri
4 | 11.4 | Testing and validation | 01-Dec | 05-Dec | ○ Plan | bar: WW46 10 Mon to WW46 14 Fri; WW47 17 Mon to WW47 21 Fri; WW48 24 Mon to WW48 28 Fri; WW49 01 Mon to WW49 05 Fri; WW50 08 Mon to WW50 12 Fri; WW51 15 Mon to WW51 19 Fri